## Лист1
Weeks
Tasks | 28.11-05.12 | 06-15.12 | 16.12-20.12 | 21.12-26.12 | 27-29.12 | 30-31.12 | 01-07.01 | 10.01
Fundamental work on basic principles of 3D reconstruction
Qt plus PCL installation and some necessary libraries.
Executing the code of previous year projects.
Finding the loop holes in the programs.
Planning for improvement in previous year project
Research on point clouds alignment methods
Implementation of filtering methods
Filtering of the registered point cloud before 3D reconstruction
Meshing, hole detection, obtaining color 3D model
Test of the Final code
Preparation of final report and presentation
Defence of the project